## Planeador de Projetos
Planeador de Forms:(SplashScreen)
Selecione um período a realçar à direita. Segue-se uma legenda que descreve o gráfico. |  |  |  |  | Realce do Período: | 1 |  |  | Duração do Plano | [5 empty] | Início Real |  |  |  |  | % de Conclusão | [5 empty] | Real (para além do plano) | [7 empty] | % de Conclusão (para além do plano)
ATIVIDADE | INÍCIO DO PLANO | DURAÇÃO DO PLANO | INÍCIO REAL | DURAÇÃO REAL | PERCENTAGEM DE CONCLUSÃO | PERÍODOS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
HydraSealTest.cs | 5 | 31 | 6 | 10 | 25%
SplashMock.cs | 1 | 6 | 1 | 6 | 100%
HydraSealTest.cs | 2 | 4 | 2 | 5 | 35%
HydraAI.cs | 4 | 8 | 4 | 6 | 10%
HydraSealTest.cs | 4 | 2 | 4 | 8 | 85%
README Ritual.txt | 4 | 3 | 4 | 6 | 85%
LexiconIA | 5 | 4 | 5 | 3 | 50%
HydraSealMetadata | 5 | 2 | 5 | 5 | 60%
HydraLauncher.cs | 5 | 2 | 5 | 6 | 75%
HydraMap.txt | 6 | 5 | 6 | 7 | 100%
SplashScreenManager.cs | 6 | 1 | 5 | 8 | 60%
HydraSealTest.cs | 9 | 3 | 9 | 3 | 0%
RescueSplashFunction | 9 | 6 | 9 | 7 | 50%
HydraMediaLexicon.cs | 9 | 3 | 9 | 1 | 0%
HydraLexiconReporter.cs | 9 | 4 | 8 | 5 | 1%
LexiconViewer.cs | 10 | 5 | 10 | 3 | 80%
HydraTerminal.cs | 11 | 2 | 11 | 5 | 0%
LexiconViewer.cs | 12 | 6 | 12 | 7 | 0%
HydraLex.db | 12 | 1 | 12 | 5 | 0%
HydraMind.json | 14 | 5 | 14 | 6 | 0%
HydraRecall | 14 | 8 | 14 | 2 | 44%
IsolatedStorage | 14 | 7 | 14 | 3 | 0%
SecureString | 15 | 4 | 15 | 8 | 12%
HydraLex | 15 | 5 | 15 | 3 | 5%
HydraConfig.json | 15 | 8 | 15 | 5 | 0%
HydraSealTest.cs | 16 | 28 | 16 | 30 | 50%
SplashMock.cs | 2
HydraSealTest.cs
HydraAI.cs
HydraSealTest.cs
README Ritual.txt
LexiconIA
HydraSealMetadata
HydraLauncher.cs
HydraMap.txt
SplashScreenManager.cs
HydraSealTest.cs
RescueSplashFunction
HydraMediaLexicon.cs
HydraLexiconReporter.cs
LexiconViewer.cs
HydraTerminal.cs
LexiconViewer.cs
HydraLex.db
HydraMind.json
HydraRecall
IsolatedStorage
SecureString
HydraLex
HydraConfig.json